## Sheet1
Team Meeting Log(Pizza Project)
# | Date | Time | Place | People Attended | Issues | Note
1 | 25/9 | 3pm-5pm | graduate lab | Cheng, Zhao, Shengti, Edward | 1. Learned how to use the Virtual Studio and Github; 2. Discussed and found out questions about the requirements. | Mo wasn't present.
2 | 28/9 | 6:30-8:30 | library209 | everyone | 1. Discussed the use cases; 2. Discussed class diagram
3 | 30/9 | 7:00-9:00pm | library231 | everyone | 1. Update use cases;2. Discuss case test;3. Divided tasks
4 | 2/10 | 7-9pm-11pm | library211,305 | everyone | dicuss test test cases
5 | 3/10 | 6:30-9pm | graduate lab | everyone | finish 1.test cases2. status form3.assessment and submitted them, which is the first deliverable for this project
6 | 7/10 | 7pm-10pm | library210,211 | everyone | finished 1. decide UML software and learn how to use it;2. 5 iterations of class diagrams of entity classses
7 | 16/10 | 7pm-10pm | library209,210 | everyone | 1. discussed sequence diagrams.2. discuss class diagrams
8 | 19/10 | 7-11pm | library227 | everyone | 1. finished class diagrams and method detail design2. software product description3. sequence diagram4. full class diagram